## Instructions
Windows 10 Migration Planner – 2025
How to use this workbook:
1. Fill in Device_Inventory with every Windows 10 endpoint.
2. Upgrade_Path_Matrix & Budget_Calc will auto-summarise counts and costs.
3. Adjust yellow-highlighted inputs (licences, ESU, labour rates) in Budget_Calc.
4. Plan rollout dates in Timeline_Gantt. Durations auto-calc.
5. Track risks in Risk_Register (likelihood x impact).
Tip: If you import to Google Sheets, re-check formulas and named ranges.

## Device_Inventory
Asset_ID | User | Department | Location | Make_Model | CPU | RAM_GB | Storage_GB | Purchase_Date | Warranty_End | OS_Version | TPM_2.0 (Y/N) | Secure_Boot (Y/N) | Upgrade_Path (Upgrade/Replace/Retire) | Age_Years | Notes
126
Formulas:
Age_Years = IFERROR(DATEDIF([Purchase_Date],TODAY(),"y"),"")

## Upgrade_Path_Matrix
Upgrade_Path | Count | Avg_Device_Cost | Total_Device_Cost
Upgrade | 0 | 135 | 0
Replace | 0 | 2355 | 0
Retire | 0 | 67.5 | 0

## Budget_Calc
Item | Value | Unit
INPUTS (edit yellow cells)
Licence cost per user (Windows 11 / M365) | 120 | AUD
ESU cost per device / year (fallback) | 90 | AUD
Average labour hours per device (upgrade) | 1.5 | hrs
Engineer labour rate | 180 | AUD/hr
Average hardware replacement cost/device | 1450 | AUD
Average imaging/deployment hours/device | 135 | hrs
Upgrade cost/device (calc) | 2355 | AUD
Replace cost/device (calc) | 67.5 | AUD
Retire cost/device (calc) |  | AUD
---
TOTALS (auto) | 0
Total Upgrade Devices | 0
Total Replace Devices | 0
Total Retire Devices | 0
Total Budget (AUD) |  | AUD

## Timeline_Gantt
Task | Phase | Start_Date | End_Date | Duration_Days | Owner | Status
Inventory devices | Inventory | 2025-01-08 | 2025-01-19 | 11 | IT Ops | Not Started
Pilot upgrade | Pilot | 2025-01-22 | 2025-02-05 | 14 | IT Ops | Not Started
Dept rollout A | Rollout | 2025-02-10 | 2025-03-01 | 19 | Project Team | Not Started
Dept rollout B | Rollout | 2025-03-02 | 2025-03-20 | 18 | Project Team | Not Started
Post-migration audit | Audit | 2025-03-21 | 2025-04-05 | 15 | Security | Not Started

## Risk_Register
Risk | Likelihood (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status
0